## SOW
Attachement
Scope of Work
| Component | Task | Materials | Labor | Total
remove all trash in and out house
| Demo | remove all carpeting flooring
demo kitchen wall
demo kitchen counter
remove kitchen appliances
demo all ceiling fans
demo all light fixtures
demo existing closets in master bedroom
Exterior | Roof | roof manintenance and check the slope part, replace a roof vent cover
| siding | replace a siding vent
| Walkway | back walkway pitched, need raise/ grade, pipe out water
front walkway, need raise
| Front Porch | replace front porch pavers
kitchen :
| Plumbing | to upgrad pvc pipes accomodting new sink,
|  | faucet, | owner
|  | install a garbage disposal | owner
Interior |  | dishwasher(appliance store) | owner
hall bath:
|  | install vanity faucet, replace shower kit, | owner
toilet: replace toilet tunk parts, flange
unclogging the drain for tub and sink
master bath:
|  | vanity | owner
|  | faucet, | owner
|  | shower kit | owner
|  | toilet | owner
hardware
sliding door
basement laundry standpipe, to upgrad and install a laundy sink
| Electrical | kithchen: update _1_ outlets to GFCI | owner
|  | hall bath, to update _1_ outlets to GFCI | owner
|  | power room, update _1_ outlets to GFCI | owner
|  | 2nd floor hallway: light | owner
master bath:
wiring
|  | install 1 outlet to GFCI and switch | owner
|  | ceiling light | owner
|  | mirror lights | owner
|  | master closet: new switch and light | owner
repair a cover of junction box
install water meter jumper
need sealant, where cable enters the meter base
|  | 1 foyer/ entry light | owner
|  | _4_ living room LED lights | owner
|  | __ dinning room light | owner
|  | _4_ kitchen LED lights | owner
|  | _1_ kitchen light | owner
|  | 2 bathroom vanity lights | owner
replace ____ outlets / switches faces
| Hvac | add AC vent in 2nd floor bedroom
| Framing | fram ___ linear feet of wall of master bath
fram ___ linear feet of wall of knee wall
| Insulation | correct insulation w exposed craft paper in crawl space and garage
knee wall ?
| Drywall | hang/finsish ___ sf of dry wall on master bath
knee wall
put drywall under stairs
| Carpentry | install _3_ exterior door :
|  | entry door 36" x 80 | owner
|  | grage fire door36" x 80 | owner
|  | basement door 33"x73 | owner
replace 15 windows:
|  | 1 window in kitchen 24" x 36" 1/2 | owner
|  | 1 window in hall bathroom 24" x 36" 1/2 | owner
|  | 5 window in two bedrooms , 1st floor, 28" x 45 | owner
|  | _1_ window, 2nd floor bedroom, 30"x 49"1/2 | owner
|  | _1_ window, 2nd floor bedroom, 25 1/2 x 40 1/2 | owner
|  | 2 windows , garage | owner
|  | _4_ window 31" x12, in basement | owner
|  | trim: instrall ___ linear feet of trim, master | owner
| Cabinets / Countertops | install cabnits in kitchen | owner
|  | install 2 vanities | owner
|  | 34"1/2 single sink, hall bath | owner
|  | _30_'' single sink, master bath | owner
| Flooring | install ____ sf title floor master bath
install ____ sf title floor power room
carpeting
fix and repair from previous inspection
| oil line/unpeotected | to check / do by HVAC professional | ?
| oil line/unsliived in concrete | to get sheeved
| chimny/ connection sealing | sweep chimney. where it enters chimeny, need to be sealed around pipe where it enters chimeny
| entrance cable | need sealant, where cable enters the meter base
| wahter meter jumper | electrical contractor
| clean up | clean house at completion of renovation

## Budget
Budget of SOW and expenses
Exterior | Component | Task | Materials | Labor | Total
| Junk remove | remove the junk and trash inside and outside |  | 2000 | 2000
| Demo | dumpster | 450 |  | 450
|  | demo interior for cosmetic renovation |  | 400 | 400
kitchen: cabinet, counter, appliances
dinning room wall
fans and light fixtures
all carpet( living room, 3 bedrooms)
master room closets
| Roof | roof manintenance and check the slope part
roof cover
| Cheminy | chimney flashing
sweep chimney
| Gutters/Soffits/Fascia | clean gutters
| Siding | pressure wash exterior
| pressure wash | exterior and garage |  | 375 | 375
| Exterior Painting | paint exterior w/ 3- color paint scheme
siding
trim - garage trim
garage walls
doors/shutters
patio pilliar
| Walkway | back walkway, pitched, need raise/ grade, pipe out water |  | 330 | 330
|  | front walkway, raise |  | 75 | 75
| Front Porch | replace front porch pavers |  | 768 | 768
| Landscaping | mulch $420, 13 Cyard+ deliverd | 420 |  | 420
|  | Davide pickup+ spread |  | 790 | 790
|  | cut lawn |  | 600 | 600
|  | flowers,grass seeds, dirt 500 | 500 |  | 500
remove ivy, dead bush, debris, tirm bushes agnist the house
| Garage | adjust reverse opener& replace senser | 139 |  | 139
| Plumbing | all pluming expenses $ 6460
|  | Roug +material+inspection | 650 | 2000 | 2650
|  | finish plumbing | 560 | 1000 | 1560
|  | repairs | 600 | 1000 | 1600
|  | unclogging the drain for tub and sink |  | 250 | 250
|  | C/ O inspection repair | 150 | 250 | 400
kitchen :
to upgrad pvc pipes accomodting new sink,
|  | kithen faucet, | 190 |  | 190
|  | kitchen garbage disposal | 80 |  | 80
Interior |  | dishwasher(appliance store)
hall bath:
|  | vanity with sink | 430 |  | 430
|  | vanity faucet, replace shower kit, | 300 |  | 300
|  | toilet | 125 |  | 125
|  | mirroe | 50 |  | 50
master bath:
|  | insatll vanity with marble sink | 690 |  | 690
|  | faucet, | 169 |  | 169
|  | shower kit stall | 240 |  | 240
|  | toilet | 125 |  | 125
|  | bar + certain | 60 |  | 60
|  | shower+hardware | 150 |  | 150
|  | shower stall | 240 |  | 240
| Electrical | add resess lights/ update outletsGFCI | 500 | 1500 | 2000
|  | replace all outlets / switches faces | 200 | 600 | 800
|  | Master basth baseboard heat+ Fan | 300 |  | 300
|  | dryer heavy duty wiring | 100 | 100 | 200
|  | sub-electrical panel | 150 | 150 | 300
|  | lighting fixture |  |  | 750
|  | 1 dinning room light | 150
|  | _1_ kitchen led ceiling lights | 35
|  | 4 bathroom vanity lights | 200
|  | 2 hallway light | 40
|  | 1 hall bath ceiling light | 35 | 150
|  | 4 closet lights fixtures | 60
|  | install ____ smoke detactor through the house | 100 |  | 120
|  | install ___2_ carbon monocide detactor through | 50 |  | 50
| Hvac | replace filter | 50 |  | 50
|  | hvac duct work( he did extra havc |  | 1080 | 200
| Framing | fram 22 feet of wall of master bath | 240 | 500 | 740
|  | fram 22 feet of wall of master closet/finish/paint | 200 | 600 | 800
|  | extra doors in master room and closet | 150 | 400 | 570
| Drywall | hang/finsish _50_ sf of dry wall on master bath and knee wall | 500 | 1000 | 1500
| Carpentry | install windows + door : |  | 1350 | 1350
|  | 16 windows 2280 |  |  | 2280
|  | doors/shutters (差价） | 730
|  | entry door 36" x 80 | 300 |  | 300
|  | grage fire door36" x 80 | 150 |  | 150
water comes in basement from outside basement, door 33"x73, need to regraded outside
|  | replace 1 window in kitchen 24" x 36" 1/2 | 130
|  | replace1 window in hall bathroom 24" x 36" 1/2 | 130
|  | replace 5 window in two bedrooms , 1st floor, 28" x 45 | 650
|  | replace _1_ window to Egress, 2nd floor bedroom, 30"x 49"1/2 | 250
|  | replace _1_ window, 2nd floor bedroom, 25 1/2 x 40 1/2 | 130
|  | replace 2 window in garage | 260
|  | living room crown moding | 100 | 200 | 300
|  | trim: instrall _60_ linear feet of trim | 200 | 200 | 400
|  | a master vanity 60'' | 689 |  | 689
|  | add kitchen base cabinate | 115 |  | 115
|  | 38 sf granite for kitchen. $39/sf, $ 1314 | 2000 |  | 2320
|  | __6_ sf of granite counter top, hall bath | 430 |  | 430
| Painting | steam remove existing wall paper, paint all rooms, cailing and trims, including garage wall, patio posts | 1400 | 1400 | 2800
|  | refinsish kitchen cabines & paint ( BEHR Papier blance) | 500 | 1500 | 2000
sand and paint existing doors
|  | to paint basement wall & floor | 180 | 350 | 850
350
| Flooring | install _____ sf / sy of carpent / pad |  |  | 3015
|  | finish 308 sf oak hard wood floor | 0 | 1500 | 800
|  | refinish Hw stairs |  |  | 700
|  | install ____ sf title( 2 floor bathroom) |  |  | 440
| hardwares | kitchen handles, 24 | 80 |  | 89
|  | kitchen hinges , 16 pair(33) | 60 |  | 60
|  | dawer slides, 6 pair |  |  | 100
| Permit | permits from parlmer township | 289.5 |  | 289
wait time for _3__ inspections
| Appliances | purchase/ install appliances:
|  | range | 560 |  | 560
|  | dishwasher | 310 |  | 310
|  | microwave | 210 |  | 220
|  | cord | 25 |  | 25
| other repairs | chimney flashing/connection sealing.window well
| Miscellameous | clean house at completion of renovation | 1000
45128

## Sheet1
Schedule of Work
Total 34Weeks | w0 | w1 |  | w2 |  | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 |  | w13 |  | w14 |  | w15 | w16 | w17 | w18 | w19 | w20 | w21 |  | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 |  | w30 | w31 | w33 |  | w34
stage1:
Immediate Concerns紧急工作
Exerior / Interior: 4Weeks | [5 empty] | w5: 9
1. survey, plans, permits测绘，许可证 | Full Review 3-4 weeks
2. dumpster/ PortaPotty清除垃圾 |  | 0.5
4. Waterproofing屋顶防水 |  |  | 0.5
5. Mold remediation处理霉菌 |  |  |  | 0.5
6.Termite / pest control消除白蚁 |  |  |  | 0.5
7. Tree removal / Grading 移除树木 |  |  |  |  | 0.5
8. Septic | [5 empty] | w5: 3
stage 2:
Rough Work
Exterior: 5～7Weeks | [17 empty] | 8 | bar: w6 to w12
9. site prep / concrete 混凝土工程 | [5 empty] | w8: 3
10. Exterior framing室外 | [5 empty] | w11: 3
11. Windows入户门 | [5 empty] | w12: 0.5
12. Siding / Trim 外墙修补 | [15 empty] | 0.5
13. Roof 屋顶修补 | [16 empty] | 0.5
14. Gutters / Soffit/ Fascia 屋顶水槽安装 | [17 empty] | 0.5
Interior: 6weeks | [23 empty] | 5.5
15. Demo 拆除室内墙 | [18 empty] | 0.5
16. Framing / Subfloor 隔断/地板龙骨 | [19 empty] | 1
17. Rough electrical 电路排线 | [20 empty] | 1
18. Rough Plumbing上下 水管安装 | [21 empty] | 1
19. Rough HVAC 采暖、空调线路 | [22 empty] | 1
20. Rough Inspection 验收 | [23 empty] | 1
Stage 3:
Unfinished Work
Exterior: 2weeks | [25 empty] | 1.5
21. Decks / Porch 室外平台搭建 | [24 empty] | 1
22. Garage 车库门安装 | [25 empty] | 0.5
Interior: 6～7weeks | [31 empty] | 4.5
23. Fireplace 壁炉 | [26 empty] | 0.5
24. Insulation 保温材料安装 | [27 empty] | 0.5
25. Insulation Inspection 保温工程验收 | [28 empty] | 1
26. Sheetrock灰板 | [29 empty] | 1
27. Doors 室内门 | [30 empty] | 0.5
28. Carpentry / Trim 地板及踢脚线 | [31 empty] | 1
Stage 4:
Finished Work | [33 empty] | 1.5
Exterior: 1-2weeks | [32 empty] | 0.5
29. Exterior Paint 室外涂料 | [33 empty] | 1
30. Landscaping 园艺工程
Interior: 6-7Weeks | [41 empty] | 6
31. interior paint 内墙涂料 | [34 empty] | 1
32. Cabinets / Countertops 橱柜/岛台安装 | [35 empty] | 0.5
33. Finish Electriccl 电线收尾 | [36 empty] | 0.5
34. Finish Plumbing 上下水收尾 | [36 empty] | 0.5
35. Finish HVAC 暖气、空调收尾 | [36 empty] | 0.5
36. Flooring 铺地板 | [37 empty] | 1
37. Title 贴瓷砖 | [38 empty] | 1
38. Appliances 电器安装 | [39 empty] | 0.5
39. Misc / Punch | [40 empty] | 0.5
40. Finial Inspections 总验收 | [41 empty] | 1