## Project Timeline
project timeline
Start Date: | 2021-03-03
| week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4 | [6 empty] | week 5 | [6 empty] | week 6 | [6 empty] | week 7 | [6 empty] | week 8 | [6 empty] | week 9 | [6 empty] | week 10 | [6 empty] | week 11 | [6 empty] | week 12
| 3月 | [6 empty] | 3月 | [6 empty] | 3月 | [6 empty] | 3月 | [6 empty] | 3月 | 4月 | [5 empty] | 4月 | [6 empty] | 4月 | [6 empty] | 4月 | [6 empty] | 4月 |  |  | 5月 |  |  |  | 5月 | [6 empty] | 5月 | [6 empty] | 5月
| 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二 | 周三 | 周四 | 周五 | 周六 | 周日 | 周一 | 周二
Assigned to: | time axis 2021-03-03 to 2021-05-25
GC Team | 2021-03-03: O1.Already Got Permit; 2021-04-07: I12.Add insulation; 2021-04-18: I9. Paint Interior; 2021-04-27: I13.Kitchen; 2021-05-02: I14.New appliances
GC Team | 2021-03-03: E1.Haul away trash; 2021-03-07: I1&I2.Demo Interior and open up kitchen wall; 2021-03-16: I2. Exterior doors (3); 2021-03-28: I11.Remodel bathrooms; 2021-04-08: I5.Repair and add drywall; 2021-04-13: I8.Replace Interior doors (10); 2021-04-21: I6. New EVP; 2021-04-25: I7. New carpet; 2021-04-29: I10.New light/fan fixtures; 2021-05-02: E3&E4.Power wash and paint exterior
Electrician (2~3) | 2021-03-14: I3.Replace electrical system
Plumbing (2~3) | 2021-03-21: I4.Replace plumbing system
Landscaping | 2021-03-14: E5.Landscaping (cut trees and eye sore); 2021-04-25: E5.Landscaping final
Final Inspection

## Work Items
Work Items:
Exterior Work
1, Haul away trash
2, Replace three exterior doors (3)
3, Power wash and paint house exterior, including siding, trim, doors, soffits, fascia, shutters, gutters, downspouts using 3-color paint scheme.
4, Power wash front porch and driveway
5, Landscaping: trim bushes around the house, trim overgrown tree in the front and back yards, patch grass if needed
Interior Work
1, Demo interior
(1) Demo cabinets, counters, appliances and fixtures
(2) Demo wallpaper and flooring
(3) Demo bathroom
2, Framing: open up kitchen wall
3, Replace whole electrical system, including new electrical panel, meter and new wiring
4, Replace the plumbing system throughout house
5, Replace drywall if needed
6, New EVP flooring in non-bedroom areas, including kitchen, bathrooms, living room
7. New carpet in the bedrooms
8, Replace Interior Doors (10)
9, Paint Entire Interior (Ceilings, Wall, Trim) Using 3-Color Paint Scheme
10, Replace all lighting (12)/fan fixtures (4)
11, Remodel bathrooms (2.5)
12, Add insulation
13, Install kitchen cabinets, countertop and accessories
14, Install new appliances (Refrigerator, Stove, Microwave, Dishwasher, Washer, Dryer)
Other:
1, Get permit