## Sheet1
1500 sqf House Rehab on 4/12 2020 to 5/16/2020
| DIY hours of 2 person | Item (Person 1) | Item (Person 2) | Paid labor work |  |  | Material cost
2020-04-09 | 2 | clean | clean windows | install front porch shingle | 150 | 2020-04-18 | underlayment | 119.05
2020-04-10 | 4 | clean | clean door | AC service | 140 | 2020-04-18 | laminate (note: on sale, 400 sqft) | 273.11
2020-04-11 | 2.5 | clean | off carpets | dump roof trash | 50 | 2020-04-26 | bathroom faucets ,floor, roof nail | 48.77
2020-04-12 | 2.5 | clean | off carpets | Total | 340 | 2020-04-28 | board,nail | 78.14
2020-04-15 | 2.5 | cut yard tree off | cut yard tree off |  |  | 2020-04-28 | nail | 12.7
2020-04-16 | 3.5 | take floor nails off | wash siding |  |  | 2020-04-29 | flashing | 5.06
2020-04-17 | 4.5 | take floor nails off | wash siding |  |  | 2020-04-30 | board | 10
2020-04-18 | 3 | buy,deliver floor |  |  |  | 2020-05-01 | shingle | 187
2020-04-19 | 3 | cut grass , fill wall |  |  |  | 2020-05-03 | bathroom sink bowl | 40.74
2020-04-20 | 5 | install floor | clean floor |  |  |  | 2 toilets | 142.2
2020-04-21 | 4.5 | install floor | clean shelves |  |  | 2020-04-04 | toilet connection part | 16.02
2020-04-22 | 4.5 | install floor | clean wall |  |  |  |  | -30
2010-04-23 | 4.5 | install floor | clean wall |  |  | 2020-05-05 | sink connection | 32
2020-04-24 | 5.5 | install floor | clean refrigarator |  |  | 2020-05-06 | deck paint, caulking | 23.3
2020-04-25 | 5 | make floor transition |  |  |  | 2020-05-05 | shoe molding | 19
2020-04-26 | 5 | install transition | house roof maintenance |  |  | 2020-05-01 | speeline, cut grass | 8.63
2020-04-27 | 5 | install transition | roof metain |  |  | 2020-05-09 | paint and roof caulk | 28
2020-04-28 | 7 | tear out old porch roof single |  |  |  | 2020-05-14 | light | 6.6
2020-04-29 | 11 | tear off old porch roof planks board |  |  |  | 2020-05-15 | key | 5.5
2020-04-30 | 5 | install porch planks board |  |  |  | 2020-05-12 | light , shoe molding | 13
2020-05-01 | 4 | install porch planks board |  |  |  |  | 15 tons abc blue slate gravel | 432.45
2020-05-03 | 3.5 | replace master bathroom 2 faucets | [5 empty] | 1471.27
2020-05-04 | 4 | install one faucet in hall way bathroom | replace bath sink bowl and toilet
2020-05-05 | 3 | fix toilet connect leaking | caulking dry wall | Actually Total DIY Cost | 1811.27
2020-05-07 | 4.5 | install one toilet in hallway bathroom | test dishwasher, water heater | DIY hours 2 person | 155
2020-05-08 | 4 | dry wall | cap toilet nail , saw short nail | parking area work expert estimate (chose to DIY in the end) | 2500 and 3500 same mateiral
2020-05-09 | 4 | touch paint whole | reinstalled toilet,caulk roof | someone estimate (chose to DIY in the end) | front porch roof replace 220 sqf $2500
2020-05-11 | 3 | fix kitchen light,pressure wash side deck |  |  | house roof maintenance $660
2020-05-12 | 4 | install light fixture, island plug | island corner trim
2020-05-13 | 6 | paint deck trim
2020-05-14 | 8 | paint deck
2020-05-15 | 6 | clean out, install corner round.
2020-05-16 | 4 | replace front door lock , repair closet shelves
| 7.5 | front house prepare for gravel parking
Total hours | 155